## iOS App
No | Date Time | Issue | Details | Additional Info | Severity | Status | Updated Date | Notes
1 | 2022-05-31 | Invalid wording | Wording on toast message doesn't meet with the design. Step: 1. Login/Register (input HP no) 2. Input invalid code or leave it blank 3. Verify | app ver. 3.5.0 (235) | Low | Fixing
2 | 2022-05-31 | No empty state | Notification menu | app ver. 3.5.0 (235) | Low | Fixing
3 | 2022-05-31 17:59 | No verification email was received | I didn't receive a verification email when verifying the email. Step: 1. Access My Account 2. Edit Profile 3. Tap icon to verify email | app ver. 3.5.0 (235) | Medium | Solved | 2022-06-02
4 | 2022-05-31 18:03 | Invalid HP No validation | I can't input 8 digits of HP No Step: 1. Access My Account 2. Edit Profile 3. Input 8 digits of HP No | app ver. 3.5.0 (235) | Medium | Fixing |  | The validation is less than 8 and more than 15 characters *riki 2June: re-update status to New
5 | 2022-05-31 18:12 | Invalid wording | Your History' title should be 'My History' Step: 1. Access My Account 2. My Spurr Activity | app ver. 3.5.0 (235) | Low | Fixing
6 | 2022-05-31 18:15 | Inaccurate search | I input 'M' on the search field, but the merchant without 'M' displayed on search result Step: 1. Access Home 2. Add New Card 3. Search card | app ver. 3.5.0 (235) | Low | Not Bug |  | Keyword is search on: merchantName merchantBrand merchantLocation merchantAddress
7 | 2022-06-02 10:00 | Offer Notification | 1. On CVM, birthday offer was set to be started on 27 June 2022 2. My birthday account is June. 3. 2 June I got a notification that I earned an offer (birthday offer), even though the offer hasn't started yet expected: I get a notification on 27 June 2022 (when the offer is active) | app ver. 3.5.0 (235) Merchant: Cendolan User: 08111399209 | High | Fixing |  | API
8 | 2022-06-02 13:00 | Loyalty card doesn't exist in Add New Card menu | I want to add 'Namsan Course' loyalty card, when accessing 'Add New Card' menu at the Homepage.. I didn't find 'Namsan Course' there, but if accessing 'Discover' menu I found it. expected: I can find 'Namsam Course' at the "Add New Card' menu. | app ver. 3.5.0 (235) Merchant: Namsam Course User: 08111399209 | Medium | Fixing |  | API
9 | 2022-06-02 14:00 | Misplaced number on Customer Priority progress bar | Conditions: I collected 2 stamps 1. Go to Loyalty Details page 2. Go to Priority Customer *refer to capture beside → | app ver. 3.5.0 (235) Merchant: Cendolan User: 08111399209 | Medium | Fixing
10 | 2022-06-03 13:45 | Invalid rewards number | in the Add Loyalty Card menu, merchant 'Clarice Beauty' has 10 rewards, but in the Brand Details it has 16 rewards | app ver. 3.5.0 (235) Merchant: Clarice Beauty User: 08111399209 | Medium | Need Test |  | Test on Dev
11 | 2022-06-03 14:25 | Can't tap the reward details | In the Reward Store for a specific merchant, I can't tap the reward to view the details. 1. Go to Reward Store 2. Go to 'See All' of specific merchant 3. Tap the reward | app ver. 3.5.0 (235) Merchant: macaronay User: 08111399209 | High | Need Test
12 | 2022-06-03 14:30 | Resend Code Timer | When the timer is running (eg at 1:30 minutes), then I switch to another application (eg open Instagram for 3 minutes), the timer seems to pause and resumes the tier when I return to the spurr app. 1. Input HP No at Login page 2. Landing at verification page and timer is running 3. Switch to another app for a few minutes 4. Back to Spurr app | app ver. 3.5.0 (235) User: 08111399209 | Medium | Fixing

## Android App
| Date Time | Issue | Details | Additional Info | Severity | Status | Updated Date | Notes
1 | 2022-06-08 | Information label doesn't match. | Wording on toast message doesn't meet with the design. The wording should be blablabla. Step: 1. Login/Register (input HP no). 2. Input invalid code or leave it blank. 3. Verify. | app ver. 3.5.0 (235) account num: +628111.... merchant: merchant name | Low | Need Test
2 | 2022-06-08 | Uppercase and lowercase letters are not the same. All must be in Indonesian language. | Details : Uppercase and lowercase letters are not the same. Expected : The wording should be "nomor handphone". Step : 1. As member account. 2. Go to the login page. 3. Check the login button. 4. The login button the letters are uppercase. | app ver. 3.3.19 account num: +62811111013 | Low | Need Test
3 | 2022-06-08 | The input label of the phone number in Malaysian does not match. All must be in malaysian language. | Details : The input label of the phone number in Malaysian does not match. Expected : The label should be "Phone number" Step : 1. As member account 2. Go to the login page 3. Check the input field 4. The login button the letters are uppercase | app ver. 3.3.19 account num: +62811111012 | Low | Need Test
4 | 2022-06-08 | Uppercase and lowercase letters are not the same, wrong punctuation. Sentence error in language. All must be in Indonesian language. | Details : Uppercase and lowercase letters are not the same, wrong punctuation. Sentence error in language. Expected : If you press the wrong number OTP The wording should be "terjadi kesalahan." The wording should be in indonesian language "Kamu memasukkan kode yang salah, pastikan kamu memasukkan kode yang benar." Step : 1. As member account. 2. Go to the 'signup/login page' then go to 'OTP page'. 3. Appears above the spur logo when you press the wrong number OTP. | app ver. 3.3.19 account num: +62811111013 | Low | Need Test
5 | 2022-06-08 | The uppercase and lowercase letters are not appropriate in Malaysian. All must be malaysian language. | Details : The uppercase and lowercase letters are not appropriate in Malaysian. Expected : It should be "Teruskan dengan nombor telefon bimbit" Step : 1. As member account 2. Go to the log in page 3. Check the login button 4. The login button "Teruskan dengan Nomor Telefon Bimbit". | app ver. 3.3.19 Account num: +62811111012 | Low | Need Test
6 | 2022-06-08 | Wrong punctiation. Wrong language. Uppercase and lowercase letters are not the same. All must be in Indonesian language. | Details : Wrong punctiation. Wrong language. Uppercase and lowercase letters are not the same. Expected : The wording should be "Selamat datang di spurr". The wording description should be "hadiah". The wording description should be "Brand". Step : 1. As member account. 2. After create a new account then go to the Tip 1 page the title "Selamat datang di Spurr." the description "reward","Brand". | app ver. 3.3.19 account num: +62811111013 | Low | Need Test
7 | 2022-06-08 | There is no option to send suggestions in the information section. All must be in malaysian language. | Details : There is no option to send suggestions in the information section. Expected : There should be a "Hantar maklumbalas" option in the information section. Step : 1. Go to the my account page. 2. Check the information section. | app ver. 3.3.19 account num: +62811111012 | Low | Solved |  | The feedback feature is no longer present in the latest version App ver. 3.3.21
8 | 2022-06-08 | Wrong sentence. Uppercase and lowercase letters are not the same. All must be in Indonesian language. | Details : Wrong sentence. Uppercase and lowercase letters are not the same. Expected : The Wording description should be "Klaim stampel atau kumpulkan poin dari Brand yang berpartisipasi untuk mendapatkan hadiah dan penawaran eksklusif." Step : 1. As member account 2. after 'Tip page 1' go to the 'Tip 2 page' The wrong description is "Klaim stampel atau akumulasi belanjaanmu dari brand yang ada dan dapatkan hadiah dan penawaran ekslusif. | app ver. 3.3.19 account num: +62811111013 | Low | Need Test
9 | 2022-06-08 | Wrong sentence in the home menu section. All must be in malaysian language. | Details : Wrong sentence in the home menu section. Expected : The description should be "Anda boleh menemui semua kad kesetiaan aktif anda, tawaran peribadi dan ganjaran di sini". Step : 1. As member account. 2. When create a new account then go to the home page. | app ver.3.3.19 account num : +62811111012 | Low | Need Test
10 | 2022-06-08 | Wrong sentence. Wrong punctiation. All must be in Indonesian language. | Details : Wrong sentence. Wrong punctiation. Expected : The wording should be "hak istimewa" The wording should be "tingkat membership" Step : 1. As member account 2. After 'Tip 2 page' go to the Tip 3 page 3. In Tip 3 page the wrong word is : "hak istimewa kamu" the sentence should be "hak istimewa". "tingkat keanggotaan" the sentence should be "tingkat membership" | app ver. 3.3.19 account num: +62811111013 | Low | Need Test
11 | 2022-06-08 | Wrong language. All must be in malaysian language. | Details : Wrong language Expected : The wording should be "Ganjaran" Step : 1. As member account 2. Go to the My Account page 3. Check the Aktiviti Spurr Saya page | app ver 3.3.19 account num : +62811111012 | Low | Solved
12 | 2022-06-08 | Wrong sentence. Wrong punctiation. Uppercase and lowercase letters are not the same. All must be in Indonesian language. | Details : Wrong sentence Expected : The wording should be "Cukup pindai kode QR kamu" The wording should be "Izinkan staff merchant untuk memproses klaim kamu atas stempel, poin, penawaran, dan reward dengan memindai kode QR Spurr." Step : 1. Log in 2. Enter phone number and otp code 3. Swipe left all the way to the last page | app ver. 3.3.19 account num: +62811111013 | Low | Need Test
13 | 2022-06-08 | Wrong sentence. All must be in Indonesian language. | Details : Wrong sentence Expected : The wording should be "Reward, Promo & Loyalti" The description should be "Semua kartu loyalti aktif, penawaran ekslusif dan reward kamu dapat ditemukan di sini." Step : 1. As member account 2. Go to Home page | app ver. 3.3.19 account num: +62811111013 | Low | Need Test
14 | 2022-06-08 | Wrong sentence. All must be in Indonesian langauge." | Details : Wrong sentence Expected : The sentence in the title should be "Akun saya" The wording should be "Bulan kelahiran" The wording should be "Aktivitas spurr saya" Step : 1. As member account 2. Go to My Account page 3. Look at 'my profile' line 4. And check on 'my spurr activity' section | app ver 3.3.19 account num: +62811111013 | Low | Need Test
15 | 2022-06-08 | Wrong language. All must be in indonesian language. | Details: As member account, if you go to the account, and click about spurr, it would show error message content key 'android version' Expected: The message for that error message should be 'Unfriendly massage' Step : 1.You login as member account. 2. Go to the account page. 3. Click about spurr 4. It would show error message. | app ver. 3.3.19 account num: +62811111013 | High | Need Test

## Partners
No | Date Time | Issue | Details | Additional Info | Severity | Status | Updated Date | Notes
1 | 8 Juni 2022 | Before add the card and then scan the QR code, it would show error message 'stampId' bla bla bla | Details : Uppercase and lowercase letters are not the same Expected : Without adding the card from the customers side, scaning the qr would be fine and success¦ . Step: 1. as member account 1. click discover, merchant appear or you search merchant 2. Don't click the add card 4. click the rewards, and click the show qr code 5. As product partners, scan the qr code. 6. It would show error message. | app ver. 3.3.19 account num: +628199008127
2 | 15 Juni 2022 | Sentence error when entering Mobile Number less than 8 characters and displaying error information that appears | Details : The error information that appears is not appropriate Expected : The sentence should be "Mobile Number must be at least 8 characters long (include country code)" Step : 1. The user's position on the Issue Stamps page 2. Click the Mobile Number input field on the Issue Stamps page 3. Enter the Mobile Number less than 8 characters 4. Click the "Issue Stamp(s)" button | app ver. 3.4 account num: +628199008127 | Low | New
3 | 15 Juni 2022 | Sentence errors in the content of the message in the information tooltip | Details : Error of message content when entering Mobile Numbers longer than 19 characters after click the "Issue Stamp(s)" button Expected : The sentence should be "Mobile Number cannot be more than 19 characters (include country code)" Step : 1. The user's position on the Issue Stamps page 2. Click the Mobile Number input field on the Issue Stamps page 3. Enter the Mobile Number more than 15 characters 4. Click the "Issue Stamp(s)" button | app ver. 3.4 account num: +628199008127 | Low | New
4 | 15 Juni 2022 | Sentence errors in the content of the message in the information tooltip | Details : Sentence error in displaying tooltip information after click the "Issue Stamp(s)" button by blanking the phone number Expected : The sentence should be "Mobile Number can't be empty" Step : 1. The user's position on the Issue Stamps page 2. Leave the phone number input field on the issue stamp blank 3. Enter Amount Spent 4. Click the "Issue Stamp (s)" button | app ver. 3.4 account num: +628199008127 | Low | New
5 | 15 Juni 2022 | Sentence errors in the content of the message in the information tooltip | Details : Sentence error in displaying tooltip information after click the "Issue Stamp(s)" button by blanking the Amount spend Expected : The sentence should be "Amount can't be empty" Step : 1. The user's position on the Issue Stamps page 2. Click the Mobile Number input field on the issue Stamp page, and then enter the phone number 3. Do didn't fill in Amount Spent 4. Click the "Issue Stamp (s)" button | app ver. 3.4 account num: +628199008127 | Low | New
6 | 16 Juni 2022 | The feeling of the sentence of the message content at the time of the display of the information tooltip appears | Details : Sentence error on the error information tooltip after click the "Issue Point(s)" Expected : The sentence should be "Amount can't be empty" Step : 1. The user's position on the Activity History page 2. Click the Scanner icon button 3. Scan QR Code 4. Click the Amount Spent input field 5. Do didn't fill in Amount Spent 6. Click the "Issue Stamp(s)" button | app ver. 3.4 account num: +628199008127 | Low | New
7 | 16 Juni 2022 | Sentence errors in the content of the message in the information tooltip | Details : Sentence error in the content of the message when the tooltip information appears Expected : The sentence should be "Amount can't be empty" Step : 1. The user's position on the Edit Stamps Issued page 2. Have a Stamp transaction 3. Click the Amount Spent input field 4. Leave the Amount Spent field blank 5. Click the "Sumbit" button | app ver. 3.4 account num: +628199008127 | Low | New
8 | 16 Juni 2022 | Sentence errors in the content of the message in the information tooltip | Details : Sentence error in the content of the message when the tooltip information appears Expected : The sentence should be "Amount can't be empty" Step : 1. The user's position on the Edit Points Issued page 2. Have a Point transaction 3. Click the Amount Spent input field 4. Leave the Amount Spent field blank 5. Click the "Sumbit" button | app ver. 3.4 account num: +628199008127 | Low | New
9 | 17 Juni 2022 | Sentence errors in the content of the message in the information tooltip | Details : Sentence error in the content of the message when the tooltip information apppears Expected : The sentence should be "Amount can't be empty" Step : 1. The user's position on the Offer Issued page 2. Have Offer transaction 3. Click the "Edit" button on the Offers Issued page 4. Click the Amount Spent input field on the Edit Offers Issued page 5. Leave the Amount Spent field blank 6. Click the "Submit" button | app ver. 3.4 account num: +628199008127 | Low | New
10 | 17 Juni 2022 | The name label on forgotten password does not match | Details : Name tag forgot password does not match Expected : The name tag should be "Forgot password" Step : 1. The user's position on the Activity History page 2. Click the Profile icon on Toolbar page 3. Click the "Edit" button on the Profile page 4. Click the "Forgot Password" button on the Edit Profile page | app ver. 3.4 account num: +628199008127 | Low | New
11 | 04 Juli 2022 | Label error on button | Details : Label error on the button in the pop up error Expected : The "Got It" button can be clicked and automatically force closing the App Step : 1. Internet connection is off 2. The user's position on the Device Menu 3. Click on the product Partners App in the Device Menu | app ver 3.9 Account num : +628199008127 | Low | New